## Slide 1
TECHCORP ENTERPRISES
IAM Platform Implementation Plan
A phased roadmap for secure identity lifecycle management, access control, and enterprise integration
Tata Consultancy Services Cybersecurity Analyst Simulation
1

## Slide 2
1. Executive summary
Context and outcomes for the proposed IAM implementation
2
TechCorp's context
Global operations across 100+ countries
150,000+ employees and a broad digital footprint
Legacy applications, third-party services, and cloud systems
Priority gaps: lifecycle automation and stronger access controls
Target outcomes
Reduce access risk
Least privilege, MFA, access reviews
Automate lifecycle
Reliable joiner, mover, leaver workflows
Integrate systems
Consistent identity controls across apps
Improve usability
SSO and clear access request flows
Design principle: centralized governance with phased, risk-based implementation.

## Slide 3
2. Proposed target architecture
Conceptual view — validate products and integrations during discovery
3
Authoritative sources
HR / contractor records
IAM / IGA core
Identity lifecycle + policy
Identity provider
SSO + MFA + federation
Provisioning & connectors
Directories, APIs, SCIM where supported
On-prem / legacy apps
SaaS / third-party apps
Cloud platforms
Privileged systems
Cross-cutting controls: RBAC • least privilege • approvals • access certification • audit logging • monitoring
Integration options depend on system support: SAML / OIDC for federation, SCIM or APIs for provisioning, LDAP / directory connectors where appropriate.

## Slide 4
3. Implementation roadmap
Indicative 20-week plan; confirm scope and staffing before committing dates
4
1. Discover
Weeks 1–3 Inventory apps, identities, roles, risks; confirm owners and requirements.
2. Design
Weeks 4–6 Define architecture, role model, lifecycle rules, MFA/SSO policies.
3. Pilot
Weeks 7–10 Connect HR source, directory, and selected low/medium-risk apps.
4. Roll out
Weeks 11–16 Expand integrations; enforce MFA; automate joiner/mover/leaver flows.
5. Optimise
Weeks 17–20 Review metrics, remediate gaps, tune policies, hand over operations.
Milestone gates: requirements approved → design signed off → pilot passes security/UAT → rollout approved → operational handover.
Timeline is an initial planning estimate, not a commitment; dependencies and application complexity may change it.

## Slide 5
4. Workstreams and implementation details
Translate the Task 3 IAM design into operational controls
5
Identity lifecycle
• HR-triggered account creation • Role-change access reconciliation • Prompt leaver disablement • Contractor sponsor and expiry
Access control
• RBAC role catalogue • Least-privilege defaults • MFA for sensitive access • Separate privileged accounts
Governance
• Manager / owner approvals • Periodic access certification • Audit logs and alerting • Exception tracking
People and resources
IAM architect / project lead
IAM engineer and integration specialists
HR, application, cloud, security, and compliance owners
Service desk, testing, and change-management support
Technology capabilities
IAM / IGA platform and authoritative identity source
Identity provider with SSO and MFA
Application connectors, APIs, and supported standards
Central logging, monitoring, test and staging environments

## Slide 6
5. Integration challenges and mitigations
Plan for heterogeneous systems, data consistency, and user impact
6
Challenge | Potential impact | Mitigation
Legacy applications | May lack modern federation or provisioning interfaces. | Use supported adapters or a controlled workflow; isolate exceptions and log manual actions.
SaaS / third-party apps | Different SAML/OIDC and provisioning capabilities. | Classify apps by support; standardize patterns and validate vendor configuration.
Cloud and hybrid systems | Permission sprawl and inconsistent policy enforcement. | Use central federation, scoped roles, cloud permission reviews, and centralized audit events.
Identity data quality | Duplicate identities or stale attributes can create incorrect access. | Define authoritative attributes, reconciliation rules, data owners, and exception queues.
Availability / rollout risk | An outage or poor configuration could block legitimate access. | Pilot in waves, test rollback, monitor sign-in failures, and maintain controlled break-glass access.
Standards are selected per capability: SAML/OIDC for sign-in federation; SCIM/APIs for provisioning where supported.

## Slide 7
6. Testing, security assurance, and deployment
No production rollout until defined acceptance criteria are met
7
Functional testing
• Joiner / mover / leaver scenarios • Role assignment and approval paths • SSO and MFA enrolment / recovery • Provisioning failure and retry
Security testing
• Unauthorized access attempts • Least-privilege and role conflicts • Privileged account controls • Log completeness and alert routing
User acceptance
• Business-owner sign-off • Usability and support readiness • Performance and availability checks • Rollback and recovery rehearsal
Deployment controls
Pilot first, then deploy in risk-based waves
Change approval, communication, and training
Backout plan and emergency access procedure
Track defects and require sign-off at each gate
Operational handover
Runbooks, ownership, and escalation paths
Monitoring dashboards and alert thresholds
Access-review calendar and exception register
Periodic policy and integration reviews

## Slide 8
7. Success measures and business alignment
Set baselines first; agree targets with stakeholders before rollout
8
Lifecycle speed
Median provisioning time; time to disable leaver access
Access hygiene
Orphaned accounts, excessive permissions, overdue exceptions
Control coverage
MFA coverage; apps under automated provisioning; SSO adoption
Governance
Access reviews completed on time; privileged access recertified
User experience
Access-related ticket volume; sign-in failure rate
Business value: reduce unauthorized access risk, improve auditability, streamline operations, and provide consistent secure access.

## Slide 9
8. Recommendation and next steps
Proceed with a phased, risk-based implementation.
Validate the application inventory, identity sources, regulatory obligations, and current IAM capabilities.
Approve the target architecture, role model, lifecycle rules, and security policies with system owners.
Pilot a representative set of applications and test success criteria before expanding.
Use measured results to refine the rollout and transfer the service to steady-state operations.
Assumption: this is a proposed implementation plan. Products, exact timelines, and targets require discovery and stakeholder approval.
9